# EmissionLens

Industrial Emission Hotspot Detector &
Circular Alternative Recommender

A production-minded 36-hour hackathon execution plan covering product discovery, MVP scope, prototype development, data and calculation logic, frontend, backend, testing, security, deployment, demo, and post-hackathon evolution.

HackOut'26

Theme: Circular Carbon Ecosystem

Version 1.0 ¦ 11 September 2026

System architecture intentionally excluded as requested.

# 0. Document Purpose

This document is the team's implementation playbook for producing a credible prototype within 36 hours. It translates the selected problem statement into a constrained product, defines what must and must not be built, assigns work across every delivery layer, and establishes objective completion criteria.

Core product promise: A small or medium industrial business enters operational data, sees where its emissions originate, receives specific circular interventions, and compares the expected cost, carbon reduction, savings, and payback before taking action.

| No. | Section | Purpose |
| --- | --- | --- |
| 1 | Product Direction | Vision, interpretation, users and success criteria |
| 2 | MVP Definition | Mandatory, stretch and excluded scope |
| 3 | Prototype Development | Screens, flows, states and interaction requirements |
| 4 | Domain and Data Work | Inputs, emission factors, evidence and demo datasets |
| 5 | Calculation and Recommendation Logic | Transparent formulas, scoring and safeguards |
| 6 | Frontend Workstream | UI implementation and acceptance criteria |
| 7 | Backend and API Workstream | Validation, workflows and API contracts |
| 8 | Persistence and Integrity | Storage, versioning, auditability and seed data |
| 9 | Quality, Security and Ethics | Testing, privacy, safety and responsible recommendations |
| 10 | Deployment and Operations | Environments, observability and recovery |
| 11 | 36-Hour Execution Plan | Time-boxed phases, owners and exit gates |
| 12 | Demo and Pitch | Demo narrative, evidence and fallback |
| 13 | Risks and Definition of Done | Failure prevention and final acceptance |
| 14 | Post-Hackathon Roadmap | Path from prototype to production |
| 15 | Reference Projects | Related GitHub projects and safe usage guidance |

Important interpretation: “Leak point” means a hotspot in the emissions profile of a process, material, energy source, or waste stream. The 36-hour MVP does not attempt physical gas-leak detection with hardware sensors.

# 1. Product Direction

## 1.1 Working Product Name and Vision

EmissionLens is an explainable industrial decarbonization decision tool for SMEs. It converts basic operational data into an emissions baseline, identifies the largest controllable hotspots, and recommends practical circular alternatives with quantified outcomes.

## 1.2 Product Principles

Evidence before persuasion: Every result exposes its input, factor, unit, formula, and source/version.

Action over reporting: The product must explain what to change, not merely display emissions.

Honest uncertainty: Missing or estimated data lowers confidence and is visibly labelled.

SME-friendly: Use operational language such as diesel litres, electricity units, scrap kilograms, and production tonnes.

Deterministic core: Calculations and recommendation eligibility remain rule-based and testable. AI, if added, only improves input or explanation.

One convincing workflow: Complete the happy path and important failure states before adding breadth.

## 1.3 Primary Users

| User | Primary need | MVP job story |
| --- | --- | --- |
| Factory owner / operations manager | Know where emissions and avoidable costs originate | “When I enter monthly operations data, show my biggest hotspots and practical changes.” |
| Sustainability consultant | Create a defensible baseline and compare interventions | “When reviewing a client, show calculations and export a decision-ready assessment.” |
| Maintenance / process lead | Prioritize implementable process improvements | “When viewing a hotspot, show actions, expected savings, difficulty and payback.” |
| Regulator / auditor | Understand the assumptions behind reported results | “When reviewing a result, trace it back to activity data and emission factors.” |

## 1.4 Target Demo Segment

Use a small food-processing facility as the primary demonstration because it naturally contains electricity, diesel, refrigeration, transport, packaging and organic-waste hotspots. Prepare a textile unit as the secondary preset to show that the product generalizes.

## 1.5 Hackathon Success Measures

| Measure | Target by hour 36 |
| --- | --- |
| End-to-end completion | A new assessment goes from data input to report without manual database edits |
| Calculation transparency | 100% of displayed emission totals have a visible input × factor breakdown |
| Actionability | At least five recommendation rules across energy, material and waste categories |
| Scenario value | User can select an intervention and see baseline versus projected emissions, cost and payback |
| Demo reliability | Primary demo passes three consecutive rehearsals on the deployed URL |
| Performance | Seeded assessment dashboard loads in under three seconds on normal hackathon Wi-Fi |
| Quality | Critical calculation tests pass; no blocker-level errors in the primary workflow |

## 1.6 Non-Goals for the Hackathon

Certification-grade carbon accounting or a claim of regulatory approval

Physical sensor integration, continuous plant telemetry, ERP integration or automated control

Complete Scope 3 accounting across multi-tier supply chains

Country-wide emission-factor coverage

Automated procurement or implementation of recommended equipment

A trained proprietary AI model

# 2. MVP Definition and Priorities

## 2.1 P0 — Mandatory MVP

| Capability | Minimum implementation | Acceptance criterion |
| --- | --- | --- |
| Factory profile | Name, industry, location, reporting period, production quantity and unit | A user can create or load a seeded factory profile |
| Operational data intake | Guided form for electricity, fuels, materials, transport and waste | Valid entries save; invalid units and negative values are rejected |
| Emission-factor registry | Versioned factors with category, unit, geography, source label and effective date | Each calculation resolves exactly one compatible factor or shows a clear warning |
| Baseline calculation | Activity data × factor, normalized to kg or tCO₂e | Totals reconcile with category and line-item values |
| Hotspot ranking | Rank sources by absolute emissions and share of total | Top three hotspots are automatically highlighted |
| Circular recommendation engine | Rule-based interventions connected to source types and thresholds | Each hotspot receives at least one relevant, non-generic action |
| Impact scenario | Projected reduction, implementation cost band, annual savings and simple payback | User can apply/remove a scenario without changing the original baseline |
| Explainable dashboard | KPI cards, category chart, hotspot list, recommendation cards and comparison chart | No result is shown without units or supporting breakdown |
| Assessment report | Printable summary containing inputs, hotspots, actions and assumptions | Report can be printed or saved as PDF from the browser |
| Demo presets | Food-processing and textile datasets | Either preset produces a complete dashboard in one click |

## 2.2 P1 — Stretch Features

Attempt these only after all P0 acceptance criteria pass:

CSV upload with a downloadable template and row-level validation errors

Data-quality score based on completeness, source and use of estimates

Recommendation prioritization by impact, payback, feasibility and confidence

Evidence attachments for bills, meter photos or process notes

Natural-language executive summary generated from already-calculated results

English plus one vernacular-language explanation mode

Assessment comparison across two reporting periods

## 2.3 P2 — Post-Hackathon

ERP, smart-meter and IoT ingestion

Supplier-level Scope 3 workflows

Consultant organization accounts and multi-client access control

Verified factor datasets and formal audit evidence packs

Recommendation learning from measured implementation outcomes

Vendor marketplace and financing options

Scope freeze rule: At hour 18, no new P0 capability may be added. At hour 28, feature work stops entirely unless it fixes the primary demo. Blockchain, chatbots, custom model training, mobile apps and microservices are excluded from the 36-hour build.

## 2.4 What Makes This More Than a Carbon Calculator

Process-level hotspot diagnosis rather than only a total footprint

Circular alternatives tied to the actual hotspot and industrial context

Quantified before/after scenarios with cost and payback

Factor lineage, confidence and audit notes

A prioritized action plan suitable for an SME decision-maker

# 3. Prototype Development Plan

## 3.1 Prototype Objective

The prototype must prove that a non-specialist can move from raw operational activity to a defensible action plan. Build the interactive prototype directly in the selected frontend stack. A separate design prototype is optional; low-fidelity wireframes should take no longer than 60–90 minutes.

## 3.2 Required Screens

| Screen | Purpose | Required components |
| --- | --- | --- |
| 1. Welcome / Demo Selector | Start a new assessment or instantly load a preset | Product promise, new-assessment button, two demo cards, methodology link |
| 2. Factory Profile | Capture context used by calculations and recommendations | Industry, location, period, production volume, units, progress indicator |
| 3. Activity Data | Enter energy, fuels, materials, logistics and waste | Category tabs, unit-aware rows, inline validation, add/remove row, save status |
| 4. Baseline Dashboard | Communicate total footprint and major categories | Total tCO₂e, intensity per production unit, category chart, confidence badge |
| 5. Hotspot Explorer | Explain why a process is a hotspot | Ranked sources, contribution percentage, formula drawer, factor provenance |
| 6. Recommendation Workspace | Present circular interventions and support decisions | Recommendation cards, impact, cost band, savings, payback, difficulty and rationale |
| 7. Scenario Comparison | Show the effect of selected interventions | Baseline/projected bars, reduction waterfall, selected actions and editable assumptions |
| 8. Report / Action Plan | Provide a judge- and stakeholder-ready result | Executive summary, hotspots, prioritized actions, assumptions and print control |

## 3.3 Primary User Flow

Select the food-processing demo or create a factory profile.

Review pre-filled monthly activity data and correct one value.

Run the assessment and see total emissions and intensity.

Open the largest hotspot to view its exact calculation.

Select a circular alternative, adjust an adoption percentage, and compare outcomes.

Review the prioritized action plan and export the assessment.

## 3.4 Required UX States

Production-minded prototypes handle more than the happy path. Implement:

Loading and calculation-in-progress states

Empty states that explain the next action

Inline field validation with examples of accepted units

Missing-factor warning with a safe fallback or blocked calculation

Network/API error with retry

Unsaved-changes warning

Low-confidence badge for estimated or incomplete data

Responsive layout for a laptop and acceptable mobile viewing

## 3.5 Visual and Accessibility Rules

Use green for improvements, amber for uncertainty, and red only for high-impact hotspots or errors.

Never rely on colour alone; include labels, icons and values.

Display units next to every numeric value.

Use chart tooltips and a visible underlying table for key results.

Maintain keyboard access, meaningful labels and readable contrast.

Keep the executive dashboard to one screen at common laptop resolution.

## 3.6 Prototype Exit Gate

The prototype layer is complete when a teammate unfamiliar with the implementation can finish the primary flow without verbal instructions, understand the largest hotspot, explain one recommendation, and identify where the result's emission factor came from.

# 4. Domain and Data Workstream

## 4.1 Activity Data Categories

| Category | MVP inputs | Example units |
| --- | --- | --- |
| Purchased electricity | Grid electricity consumed during reporting period | kWh |
| Stationary fuel | Diesel, LPG or natural gas used in boilers/generators | L, kg, standard m³ |
| Transport | Material or product mass and distance by vehicle class | tonne-km |
| Materials | Virgin or recycled packaging/material quantities | kg or tonne |
| Waste | Waste type, quantity and current disposal route | kg or tonne |
| Refrigerants — optional P1 | Refrigerant type and leakage/refill quantity | kg |

## 4.2 Minimum Emission-Factor Fields

Unique factor identifier and human-readable name

Activity category and compatible input unit

Factor value and output unit, normally kgCO₂e per activity unit

Country/region and reporting year

Source organization, source title and URL/reference text

Version and effective date

Scope or boundary label

Quality rating and explanatory notes

## 4.3 Data Quality Rules

| Input quality | Suggested score | Meaning |
| --- | --- | --- |
| Metered or invoice-backed | 1.00 | Directly supported by primary evidence |
| Operational record | 0.85 | Recorded internally but not independently verified |
| Calculated estimate | 0.65 | Derived from production or equipment assumptions |
| Industry default | 0.40 | Fallback value; suitable only for indicative results |

Calculate an overall confidence score weighted by each line item's share of total emissions. The score communicates data reliability; it must never be presented as formal verification.

## 4.4 Demo Dataset Requirements

Seed two coherent datasets rather than random values:

Food-processing facility: high grid electricity, diesel boiler use, refrigeration, plastic packaging, inbound transport and organic waste to landfill.

Textile facility: electricity, natural gas/coal heat, virgin material, dye-process waste and transport.

For each dataset, pre-calculate an expected result in a spreadsheet or fixture file so the application output can be independently checked.

## 4.5 Data Safety and Validation

Reject negative activity quantities and unsupported units.

Apply reasonable upper-bound warnings without silently changing values.

Normalize units once and retain the original submitted value.

Never combine CO₂ with CO₂e without an explicit label.

Store the emission-factor version used in each calculation result.

Do not invent a factor when no compatible factor exists.

# 5. Calculation and Recommendation Logic

## 5.1 Baseline Formula

Line-item emissions (kgCO₂e) = activity quantity × unit-conversion multiplier × emission factor Total emissions are the sum of valid line items. Emissions intensity equals total emissions divided by production quantity.

Every line-item response must contain the original activity, normalized activity, factor value, factor unit, factor version and resulting emissions. Rounding occurs only for display, never during intermediate calculations.

## 5.2 Hotspot Detection

For the MVP, hotspot detection is deterministic:

Group emissions by process/category.

Sort sources by kgCO₂e descending.

Calculate contribution percentage.

Mark the top three sources and any single source above 20% of total.

Attach a reason label such as “largest absolute source” or “high-carbon disposal route.”

## 5.3 Circular Recommendation Knowledge Base

| Trigger | Example intervention | Outcome model |
| --- | --- | --- |
| High grid-electricity emissions | Rooftop solar, renewable PPA or load scheduling | Replace selected percentage of grid kWh with lower-factor electricity |
| High boiler fuel consumption | Waste-heat recovery, insulation or fuel switching | Reduce fuel quantity by expected efficiency percentage |
| Organic waste sent to landfill | Anaerobic digestion or composting | Avoid landfill factor, add treatment and transport factors |
| Dry biomass residue | Biochar conversion | Estimate durable carbon fraction minus conversion/transport emissions |
| Virgin plastic packaging | Recycled content or reusable packaging loop | Replace virgin-material factor with alternative factor |
| Metal scrap discarded | Closed-loop recycler partnership | Compare disposal with recovered-material pathway |
| High freight emissions | Load consolidation, local sourcing or modal shift | Change tonne-km, vehicle factor or distance |

## 5.4 Recommendation Scoring

Use normalized values between 0 and 1:

Priority score = 0.40 × reduction potential + 0.25 × payback attractiveness + 0.20 × feasibility + 0.15 × confidence

Display the components. Do not hide the score behind an AI label. Allow a user to sort by maximum carbon reduction, lowest cost or fastest payback.

## 5.5 Scenario Formulas

Projected emissions: baseline emissions − avoided emissions + new pathway emissions

Annual operating savings: avoided annual cost − new annual operating cost

Simple payback: implementation cost ÷ annual operating savings

Reduction percentage: (baseline − projected) ÷ baseline × 100

If savings are zero or negative, show “no simple payback” rather than an invalid value. Cost bands should be labelled indicative and editable.

## 5.6 AI Policy for the MVP

No trained AI model is required. If time permits, an LLM may convert deterministic results into a plain-language executive summary. The prompt must receive only calculated values and approved recommendations; the response must not create new factors, savings or claims. The application must continue working if the AI service is unavailable.

Scientific guardrail: Emission reductions are scenario estimates, not guaranteed outcomes. Biochar or other sequestration claims require explicit boundary assumptions. Display those assumptions in the report.

# 6. Frontend Workstream

## 6.1 Recommended Implementation

Use the team's strongest web stack. A practical default is Next.js or React with TypeScript, a component library, a charting library and schema validation. Reuse components and avoid building a design system during the hackathon.

## 6.2 Frontend Tasks

| Task group | Deliverables | Completion check |
| --- | --- | --- |
| Foundation | Theme tokens, page shell, navigation, API client, error boundary | Consistent layout and no duplicated request logic |
| Forms | Factory profile and category-based activity-entry components | Unit-aware validation and usable keyboard navigation |
| Dashboard | KPI cards, emissions-by-category chart, ranked hotspots | Values reconcile and charts remain readable with zero/small values |
| Explainability | Calculation drawer and factor-source display | A judge can trace a total to its source inputs in two clicks |
| Recommendations | Cards, filters, selection state and action details | Only applicable recommendations are displayed |
| Scenario planner | Editable adoption assumptions and comparison visual | Changes recalculate without mutating the baseline |
| Report | Print-friendly layout and methodology notes | Browser print preview is complete and unclipped |
| Resilience | Loading, empty, validation, API error and retry states | Primary flow never fails silently |

## 6.3 Frontend Definition of Done

☐ Primary flow works at 1366×768 and a modern mobile viewport.

☐ All charts show values, units, labels and tooltips.

☐ Form errors explain how to fix the input.

☐ Direct navigation or refresh does not lose the seeded assessment.

☐ No placeholder buttons appear in the demo path.

☐ A judge can access factor provenance and assumptions.

# 7. Backend and API Workstream

## 7.1 Backend Responsibilities

Validate and normalize factory and activity inputs.

Resolve compatible emission factors.

Run deterministic baseline and scenario calculations.

Rank hotspots and recommendations.

Persist assessments, input lines, factor references and selected actions.

Return structured errors suitable for inline frontend display.

Seed and reset demo data safely.

## 7.2 Minimum API Surface

| Operation | Purpose | Critical behavior |
| --- | --- | --- |
| Create/read assessment | Manage factory and reporting context | Stable identifier and timestamps |
| Add/update activity | Capture operational inputs | Unit validation and normalized value |
| Calculate baseline | Produce totals and line-item evidence | Idempotent for unchanged inputs |
| List hotspots | Return ranked sources | Reason and percentage included |
| List recommendations | Return eligible actions | Rule identifier and score components included |
| Evaluate scenario | Compare selected interventions | Baseline remains immutable |
| Load demo preset | Create a reliable seeded assessment | Repeatable and safe to rerun |

## 7.3 Backend Quality Requirements

Use typed request and response contracts.

Keep calculation functions pure where practical.

Return consistent error codes and user-safe messages.

Log calculation start, completion, factor version and failure without logging sensitive raw documents.

Never trust a client-calculated emissions total.

Add health and readiness endpoints if a separate backend is deployed.

# 8. Persistence and Integrity Workstream

## 8.1 Information to Persist

Factory and reporting-period metadata

Activity rows, original units, normalized values and data-quality classification

Emission-factor records and versions

Calculation runs and the factor version used by each line

Hotspot results and recommendation rule identifiers

Scenario assumptions and selected interventions

Creation/update timestamps and basic change history

## 8.2 Integrity Rules

A calculation result must be reproducible from stored inputs and factor versions.

Updating activity data creates a new calculation result rather than rewriting previous evidence.

Demo reset affects only demo assessments.

Database migrations and seed commands are committed and repeatable.

Secrets are configured through environment variables and excluded from source control.

## 8.3 Hackathon Storage Choice

Use SQLite for the fastest local/deployed prototype where the host supports persistent storage, or managed PostgreSQL/Supabase when the team already knows it. Do not introduce multiple databases, caches or queues in the MVP.

# 9. Quality, Security and Ethics

## 9.1 Testing Pyramid for 36 Hours

| Test type | Minimum coverage | Priority |
| --- | --- | --- |
| Calculation unit tests | Electricity, fuel, transport, waste, unit conversion, rounding and missing-factor behavior | Critical |
| Recommendation-rule tests | Eligible, ineligible, threshold and ranking cases | Critical |
| API integration tests | Create assessment → add data → calculate → retrieve recommendations | High |
| Frontend component tests | Validation and result formatting for the most important form/chart components | Medium |
| End-to-end smoke test | Primary demo journey on deployed environment | Critical |
| Manual exploratory test | Zero, missing, huge, decimal, wrong-unit and network-error cases | High |

## 9.2 Security Baseline

Validate all server inputs and escape user-provided display text.

Apply secure headers and a restrictive CORS policy when frontend/backend origins differ.

Never commit keys, database credentials or uploaded bills.

Limit upload type and size if evidence/CSV upload is implemented.

Return generic server errors to users and detailed errors only in protected logs.

Use demo access or minimal authentication; do not build a rushed custom password system.

## 9.3 Privacy and Ethical Safeguards

Collect only fields required for the assessment.

Mark demonstration companies and figures as synthetic.

Do not present recommendations as regulatory, engineering or investment certification.

Explain material assumptions, uncertainty and excluded boundaries.

Avoid recommendations that improve reported emissions by shifting pollution elsewhere.

Keep original and projected results distinct; never overwrite the baseline.

# 10. Deployment and Operations Workstream

## 10.1 Deployment Requirements

One-command local start documented in the README

Committed environment-variable example without secrets

Repeatable database migration and seed procedure

Deployed frontend and API or a single full-stack deployment

Stable demo URL tested from a device not used for development

Offline fallback consisting of a local build and seeded database

## 10.2 Observability

Keep observability lightweight but useful:

Structured logs for request ID, assessment ID, calculation duration and result status

Health check and visible application build/version

Client error boundary with a recovery action

Basic uptime check or manual pre-demo health checklist

No sensitive operational inputs in logs

## 10.3 Release Controls

Protect the main branch from experimental work after hour 28.

Tag or record the demo commit.

Maintain a known-good deployment URL and local fallback.

Do not upgrade dependencies during the final four hours.

# 11. Detailed 36-Hour Execution Plan

## 11.1 Suggested Team Roles

| Role | Primary ownership | Secondary ownership |
| --- | --- | --- |
| Product / integration lead | Scope, domain rules, integration, release decisions | Demo narrative and README |
| Frontend / UX developer | Forms, dashboard, scenarios and report | Accessibility and end-to-end testing |
| Backend / data developer | API, persistence, seed data and validation | Deployment and logs |
| Calculation / quality lead | Factors, formulas, recommendation rules and tests | Pitch evidence and assumptions |

For a three-person team, combine product/integration with calculation/quality. For two people, one owns product/frontend and the other backend/calculations, with shared testing and pitch work.

## 11.2 Phase Plan

| Hours | Phase | Parallel work | Exit gate |
| --- | --- | --- | --- |
| 0–2 | Alignment and scope lock | Confirm target user and demo industry; convert P0 into tasks; select stack; assign owners; define branch/merge rules | One-page scope, ordered backlog, owners, and primary demo story agreed |
| 2–5 | Domain and prototype foundation | Sketch eight screens; define activity/factor fields; create two coherent datasets; calculate expected outputs independently | Clickable skeleton or route shell; reviewed formulas and fixture results |
| 5–9 | Project foundation | Initialize frontend/backend; configure validation, database, migrations, seed command, test runner, environment variables and initial deployment | Application deploys, health check works, seeded record is readable |
| 9–14 | Data intake vertical slice | Build factory/activity forms; create persistence endpoints; implement units and factor lookup; write validation tests | A user can save valid activity data and receives useful invalid-input errors |
| 14–19 | Calculation and hotspot vertical slice | Implement pure formulas; category aggregation; intensity and hotspot ranking; dashboard KPIs and charts; calculation tests | Seeded expected totals reconcile and top hotspots render correctly |
| 19–24 | Recommendation and scenario vertical slice | Implement at least five rules; priority score; scenario calculations; recommendation UI; baseline/projected comparison | One hotspot can be converted into a transparent action scenario end to end |
| 24–28 | Explainability and report | Add factor provenance, formula drawer, confidence indicators, assumptions and print-ready action plan | A reviewer can trace results and print a complete assessment |
| 28–31 | Integration and hardening | Run API and end-to-end tests; fix state, unit and rounding issues; add errors/retries; security check; mobile/laptop check | No blocker defects; primary workflow passes twice on deployed environment |
| 31–33 | Demo production | Finalize datasets, screenshot/report assets, README, methodology, limitations and offline fallback | Demo can be reset and completed in under five minutes |
| 33–35 | Pitch and rehearsal | Prepare problem/solution/impact story; assign speaking roles; run three timed rehearsals; record backup walkthrough | Three consecutive successful demonstrations within allotted time |
| 35–36 | Freeze and submission | Tag demo commit; verify URLs; submit required assets; preserve local copy; only blocker fixes allowed | Submission receipt confirmed and known-good version preserved |

## 11.3 Phase-Level Deliverables

### Phase A — Product and Domain

☐ Target factory and reporting boundary documented

☐ P0/P1/out-of-scope list accepted by team

☐ Calculation worksheet and seed datasets reviewed

☐ Claims and limitations wording approved

### Phase B — Working Vertical Slices

☐ Input → persistence

☐ Persistence → calculation

☐ Calculation → dashboard

☐ Hotspot → recommendation

☐ Recommendation → scenario

☐ Scenario → report

### Phase C — Production-Minded Hardening

☐ Validation and explicit error states

☐ Factor version and formula traceability

☐ Calculation, integration and smoke tests

☐ Secure configuration and clean repository

☐ Deployed and offline demo paths

☐ README, assumptions and limitations

## 11.4 Decision Checkpoints

| Checkpoint | Decision |
| --- | --- |
| Hour 5 | If data and formulas are unclear, reduce categories rather than inventing factors. |
| Hour 14 | If forms are incomplete, drop CSV and finish the guided form. |
| Hour 19 | If totals do not reconcile, stop UI expansion and fix calculation correctness. |
| Hour 24 | If scenarios are unstable, support one intervention per assessment and polish it. |
| Hour 28 | Freeze features. Only quality, demo and submission work remains. |
| Hour 33 | If deployment is unreliable, switch the official demo to the tested local fallback. |

# 12. Demo and Pitch Plan

## 12.1 Four-Minute Demo Narrative

| Time | Story | Product evidence |
| --- | --- | --- |
| 0:00–0:35 | SMEs know their bills but not the emissions and circular decisions hidden inside them. | Problem slide or welcome screen |
| 0:35–1:10 | Load the food-processing facility and show familiar operational inputs. | Profile and activity data |
| 1:10–1:50 | Reveal the baseline and largest hotspot. | Dashboard and hotspot ranking |
| 1:50–2:25 | Prove transparency by opening the formula and factor source. | Calculation breakdown |
| 2:25–3:10 | Select a circular intervention and change its adoption percentage. | Recommendation and scenario comparison |
| 3:10–3:40 | Show annual CO₂ reduction, cost, savings, payback and confidence. | Impact summary |
| 3:40–4:00 | Export the action plan and state the scale-up path. | Printable report |

## 12.2 Judge Questions to Prepare

Where do the emission factors come from, and how are they versioned?

Why are the recommendations reliable if no AI model is trained?

How do you avoid greenwashing or false precision?

What happens when data is incomplete?

How does this differ from a standard carbon calculator?

How would the prototype connect with meters or ERP systems later?

Who pays for the product, and what is the adoption incentive?

## 12.3 Demo Evidence Pack

Deployed URL and local fallback

Seed/reset instructions

Expected calculation worksheet

One exported sample assessment

Methodology and limitation notes

Short screen recording in case of network failure

# 13. Risk Register and Definition of Done

## 13.1 Risk Register

| Risk | Warning sign | Mitigation |
| --- | --- | --- |
| Scope explosion | Team discusses chatbots, mobile, blockchain or sensors before baseline works | Enforce P0 and hour-18/hour-28 freezes |
| Untrustworthy factors | Values lack units, region, year or source | Use a small versioned registry and display provenance |
| Calculation mismatch | Chart totals differ from line-item totals | Single server-side calculation source and fixture tests |
| Generic recommendations | Same advice appears for every factory | Use eligibility rules and show why each action applies |
| Fake precision | Exact savings shown for estimated inputs | Use ranges, confidence and assumptions |
| Integration delay | Frontend and backend meet after hour 20 | Integrate a thin vertical slice by hour 14 |
| Deployment failure | Works only on one laptop | Deploy by hour 9 and preserve local fallback |
| Pitch overload | Demo attempts every screen | Use one factory, one hotspot and one intervention |
| AI hallucination | Generated explanation introduces unsupported numbers | AI remains optional, constrained and non-authoritative |

## 13.2 Final Definition of Done

☐ Factory data can be entered or loaded from a demo preset.

☐ Baseline emissions calculate using documented, versioned factors.

☐ Total, category and line-item values reconcile.

☐ Top hotspots are ranked and explained.

☐ At least five circular recommendation rules exist.

☐ At least one recommendation produces a complete cost/carbon scenario.

☐ Assumptions and confidence are visible.

☐ Report prints without broken layout.

☐ Critical automated tests pass.

☐ Primary deployed journey passes three rehearsals.

☐ Repository contains setup, seed, test and demo instructions.

☐ Secrets, personal data and unlicensed copied code are absent.

☐ Submission package and local fallback are preserved.

Final product test: A judge should be able to answer three questions after the demo: “Where are the emissions?”, “What should this factory change first?”, and “Why should I trust the number?”

# 14. Post-Hackathon Production Roadmap

| Stage | Goal | Key work |
| --- | --- | --- |
| Weeks 1–4: Validation | Confirm usefulness with real SMEs and consultants | User interviews, factor review, workflow analytics, usability fixes, sector selection |
| Months 2–3: Pilot | Run assessments with controlled customer data | Authentication, organizations, evidence storage, permissions, audit history, verified datasets |
| Months 4–6: Integration | Reduce manual input and measure actual outcomes | ERP/meter connectors, scheduled ingestion, baseline periods, implementation tracking |
| Months 6–12: Scale | Become a sector-specific decision platform | Industry templates, supplier data, richer scenario optimization, external assurance and reporting exports |

## 14.1 Production Features Deferred Deliberately

Strong identity, role-based access and organization isolation

Encryption and retention controls for uploaded operational evidence

Formal factor governance and expert review

Background processing and robust import pipelines

Monitoring, alerting, backups and disaster recovery

Accessibility audit, localization and regulatory assessment

Measured post-intervention verification

# 15. Related GitHub Projects

| Project | Relevant idea | Usage guidance |
| --- | --- | --- |
| preetimitrakol2000-ctrl/Demo-website-for-EcoTrace-AI | Industrial/supply-chain emissions evaluation and optimization suggestions | Study product positioning and dashboard ideas |
| mohamadtgh/sample-climate-action-recommender | Role- and industry-oriented carbon-reduction recommendations | Study recommendation presentation |
| mchangki/ai_powered_sustainability_optimization | Energy, material, waste and carbon optimization concept | Use as feature inspiration, not proof of scientific accuracy |
| kartikeyashivankar/Circular-Economy-Intelligence-Platform | Industrial waste-stream reuse and circular recommendations | Study circular-intervention categories and analytics |

Repository availability does not automatically grant permission to copy code. Review each repository's license before reuse, attribute permitted dependencies, and build an original implementation and user experience for the hackathon.

## 15.1 Final Build Recommendation

Build a narrow, trustworthy decision engine: one factory assessment, transparent emissions, three ranked hotspots, five rules, one editable scenario and one exportable action plan. Correctness, explainability and demo reliability are the winning features. AI is optional and must never become the source of numerical truth.

Prepared for HackOut'26. This plan intentionally excludes system architecture and architecture diagrams. All emissions and financial outputs in the prototype must be labelled indicative until reviewed against authoritative, current factor datasets and customer evidence.